ASPIRE LIVING · STANDARD OPERATING PROCEDURE Site Diary — Daily Completion & Submission

| Document Ref ALDS-SOP-SITE-DIARY-01 | Version 1.0 | Date June 2026 | Approved by Chris Paton |
| --- | --- | --- | --- |

# Purpose

This SOP governs how the site manager records and submits the daily site diary for each Aspire development. A consistent daily entry — progress, workforce, weather, plant, concerns and health & safety — gives an accurate, time-stamped record of each site and surfaces blockers early.

On submission the diary is filed automatically to the project’s Dropbox folder with its photos, a summary is emailed to Chris, and any health & safety entry is sent to James Staines for review.

⚠ NOTE: This diary is a daily operational record — it is NOT the formal H&S compliance evidence base. James Staines’s independent inspections remain that.

Always phone a serious incident through to James Staines immediately; never rely on the diary alone to raise it.

| STAGE 1 — Daily Site Diary | OWNER Site Mgr — Per-project site manager |
| --- | --- |

| # | Step | Detail |
| --- | --- | --- |
| 1 | Open the form | Open the Site Diary from the Site Diary tile on the ALDS hub, or the bookmarked link aspire-site-diary.netlify.app. One diary per site, per day — not per visit. |
| 2 | Project, date & site lead | Project: pick the site from the dropdown (it lists only active projects). Date: defaults to today — change only if you are writing up a previous day. Site lead: enter your own name; it must match the signature at the end. |
| 3 | Site times & weather | Enter site open and close times. Select the weather conditions, add temperature and any note (e.g. “dried out by 11am”). |
| 4 | Who was on site | Add a row per contractor: choose the firm from the dropdown (engaged & active firms on this project) and enter how many of their people attended. Use “Other” for anyone not yet in the register. Total headcount totals automatically. |
| 5 | Plant & equipment | Add any plant or equipment on site — item, supplier/owner, and status (in use / off-hire today). Skip if none. |
| 6 | Progress report | Record what got done today: areas worked, trades on site, and any key milestones hit. Be specific — this is the daily record of progress. |
| 7 | Concerns & support needed | Note anything holding the team up: material shortages, subcontractor issues, decisions needed from Chris. Capture anything the iPad sign-in won’t — no-shows, late arrivals, early finishes. |
| 8 | Attach photos, sign & submit | Add site photos for the day. Sign: type your full name — it must match the site lead entered at the top. Tap Submit. The form auto-saves as you go, so a dropped signal won’t lose your work. |

| STAGE 2 — Health & Safety Logging & Escalation | OWNER Site Mgr → JS — Site Manager / James Staines |
| --- | --- |

Complete Stage 2 whenever there has been any H&S activity on site — an induction, a toolbox talk, a near-miss — or any incident. If there is genuinely nothing to report, leave the H&S section blank and James is not notified.

| # | Step | Detail |
| --- | --- | --- |
| 1 | Complete the H&S fields | Fill the Health & Safety section: inductions given (who was inducted today), toolbox talks delivered, and any observations or near-misses — with what was done about them. |
| 2 | Record any violation / incident | In the Violations / incidents field, describe any accident, injury, unsafe act or RIDDOR-reportable event. Leave blank if there were none. |
| 3 | Phone James immediately if serious | For any accident, injury or dangerous occurrence, phone James Staines straight away — do not wait for the emailed diary. James Staines, SHEQ Solutions (compliance). |
| 4 | Submit — James auto-notified | On submit, any H&S entry is automatically emailed to James Staines (copied to Chris); an entry under Violations / incidents is flagged as an incident. James reviews and logs/actions it. |

# Quick-Reference Checklist

Tick off before leaving site. The Site Manager owns every daily item; James Staines owns the H&S follow-up.

| ✓ | Owner | Task |
| --- | --- | --- |
| ☐ | Site Manager | One diary submitted per site, per day |
| ☐ | Site Manager | Project, date and site lead correct |
| ☐ | Site Manager | Site open/close times and weather entered |
| ☐ | Site Manager | Every contractor on site logged with headcount |
| ☐ | Site Manager | Plant recorded (or none on site) |
| ☐ | Site Manager | Progress report written — specific to today |
| ☐ | Site Manager | Concerns/blockers noted (incl. no-shows, late arrivals) |
| ☐ | Site Manager | Photos attached |
| ☐ | Site Manager | H&S section completed if any inductions, talks or observations |
| ☐ | Site Manager | Any serious incident phoned to James Staines immediately |
| ☐ | Site Manager | Signed (name matches site lead) and submitted |
| ☐ | James Staines | Review H&S entries received by email |
| ☐ | James Staines | Action and log any incident to the HSEQ system |

# Document Control

| Version | Date | Author | Summary of change |
| --- | --- | --- | --- |
| 1.0 | June 2026 | Chris Paton / ALDS | Initial issue — covers the v2 site diary form, engaged-contractor picker, H&S section and Make automation. |

# Process Flow